Date:		9th June 2015 	Time:	14.00

Location:	 	The Optima, Glasgow

1. 	Welcome and apologies

Present:	Bill Maxell (chair)

Denise Brock, Education Scotland

Maureen Gore, Education Scotland

Linda Rae, Education Scotland

Alan Johnston, Scottish Government

Jean Blair, SQA

Joe Wilson, College Development Network

John Kemp, Scottish Funding Council

Ken Edwards, Skills Development Scotland (attending on behalf of David 	Cameron)

Craig Munro, ADES

Terry Lanagan, ADES

Ann Cura, Education Scotland (notes)

Janie McManus, Education Scotland (for Attainment Challenge item)

Joan MacKay, Education Scotland (for DYW item)

Apologies:	Apologies from Gill Stewart, David Cameron, Graeme Logan and Angela 			Davidson.

Welcome:	Bill welcomed Joan MacKay, who was attending the meeting for the item on

Developing the Young Workforce.

2. 	Minutes and action log of the meeting held on 18 June 2015

Agreed 1:		The minutes of the previous meeting were approved.

Noted 1:	Action Log - Actions 1, 2, 4, 6, and 7 closed

Noted 2:	Action 3 – Workshop now taking place in August 2015.

Action 8 Denise to e-mail Joe Wilson who will nominate someone from the

CDN to join the comms group.

3. 	Matters arising

Noted 1: 		There were no matters arising.

4. 		Programme Reporting

4.1 		Programme highlight report

Noted 1:	Key deliverables in the CfE Programme Plan remain on track to be completed

on time although there has been some minor slippage in specific areas

considered to be non-critical in nature.

Noted 2: 	A few key deliverables have been achieved within this period, most notably the

publication of materials for the Advanced Highers.

Action: 	Request for an update on CfE briefing for parents.  This was expected

June 2015 but the group agreed that it may be best to publish in August

2015. Action:  Maureen Gore to request an update from Maureen Mallon

for the next meeting.

4.2 		RID Log

Risks

Noted 1:	There is only one red risk (0002) at residual level and this relates to cuts in

budgets at local and national level.  The group agreed that this still merits

serious on-going attention although it was noted that local authorities remained

highly committed to CfE and it was not anticipated currently that cuts would

prevent them taking forward the next phase of implementation milestones in

line with the Implementation Plan.

Agreed 1:	The group agreed to close risk number 7.

Agreed 2:	The group agreed that risk 24 should be escalated to an issue.

Noted 2:	A new issue had been raised by the SQA.  Various factors combined which

meant that the entry patterns for the qualifications were slightly different to what

was expected.  SQA have put in place contingencies and will continue to

monitor the situation.

Noted 3:  	A discussion took place regarding the heightened political atmosphere and

consequent support for CfE.  It was suggested that a new risk be added or

incorporated into an existing risk.

Action 1:  	Maureen Gore to discuss at the SAO meeting and report back to the next

meeting.

Agreed 3:  	It was agreed that Risk 005 to be updated to include Advanced Higher

2015/16.

Issues

Agreed 4:  	The group agreed to close Issue number 008.

Action 2:  	Maureen Gore to update the RID.

Dependencies

Noted 4: 	A discussion took place regarding DYW funding.  Concerns are being raised in

Local Authorities as funding is only available for 12 months.

Agreed 5: 	The group agreed that DP-006 should remain open

Noted 5:		A dependencies workshop is scheduled for August which will look at the DYW

dependencies and Insight on Parentzone.

4.3		Milestones Table

Noted 1:  	There are a few missed milestones on the plan due to re-scheduling of specific 		pieces of work but nothing that will have a detrimental effect on the overall

status of the programme.

5. 	SQA Update

Noted 1:	Jean Blair provided an update from SQA. The marking process is now

underway. SQA have contacted the centres who have not yet submitted all

their unit results, entries, etc.  Jean assured the group that everything is where

it is expected to be at this stage of the process.

6. 	Update from CfE/DYW Workshop

Noted 1:		Alan Johnston provided the group with an update on a workshop which was

held on 27 May for stakeholders and Implementation Group members.

Noted 2: 		It was agreed this was a useful session to raise awareness in connection with

DYW and to discuss how things can be taken forward. One issue discussed

was the integration of planning so that schools and colleges can see from the

CfE implementation plan what they need to do in their centres.

Agreed: 		The group agreed that DYW should now be a standing agenda item.

Action:   		DYW to be added to the agenda at each meeting.  Action:  Ann Cura.

Noted 3: 	Standard for Work Placements and Standard for Careers Education are due to

be released in September. The documents are on the Education Scotland

website for public consultation until the end of July.

7. 	Scottish Attainment Challenge

Noted 1:	Bill welcomed Janie McManus to the meeting to provide  a presentation on

the Scottish Attainment Challenge.

Noted 2:	The following key points were highlighted:

- Scotland’s attainment record is good, and improving but unacceptably large gap persists between the attainment of our most advantaged and most disadvantaged young people.

- The Programme for Government signalled a sharpened focus on the need for improvement in educational attainment and reducing the gap.

- In support of this, First Minister then launched the Scottish Attainment Challenge, backed by a new £100m Attainment Scotland Fund.

Noted 3:	Recruitment is now underway for Attainment Advisors.  Over 100 applications

have been received. First tranche of Attainment Advisors will be recruited for                   		the seven local authorities in receipt of the Scottish Attainment Fund by end of

June 2015.

Noted 4:	Education Scotland will be establishing a new online National Improvement

Hub with a clear focus on supporting practitioners in raising the attainment of

children and young people from the most socially deprived backgrounds. This

will be a mix of on-line content and collaborative networking/professional

learning opportunities delivered in a range of on-line and face to face formats.

8. 	Inspection Advice Note 2015/16

Noted 1:	Maureen Gore provided an update regarding the Inspection Advice Note.  This

is in draft format and is currently being circulated for comment.

Noted 2:	The Inspection advice note will be released week commencing 22nd June 2015.

The main areas of focus in the report are:

- Raising Attainment for All

- Closing the Gap

- Focus on raising attainment on Literacy and Numeracy

- Skills for Learning, Life and Work

9. 	Communications and Engagement

Noted 1:	Denise Brock provided an update to the group.  Denise highlighted that this

reporting period had been a busy time due to the pre-election, post-election,

SSLN results, exam period, AGMs of stakeholder groups, etc.

Noted 2:	Looking forward to the NQ results, it was noted that this year there is more 		scope for journalists to make comparisons so there is a big task in briefing

journalists appropriately.  Meetings were being planned to look at stakeholder

comms and particularly those to parents.

Noted 3:	ADES asked for a position statement to use following the publication of the

results.    This will be issued to all Directors.

10. 		AOB

Future Meetings

Noted 1:		The group discussed the positive feedback received from previous meetings

and workshops which involved wider stakeholders beyond the IG.

Agreed: 		The group agreed that a stakeholder session included at the next

Implementation Group meeting. A number of stakeholders should be

invited, as below. This will also be an opportunity raise issues regarding

DYW.

Action:  		Letters of invitation to a stakeholder workshop to be issued to SLS,

AHDS, EIS, SSTA , NPFS, SPTC to be invited to attend.

Time of the next meeting to be changed to start at 09.00 hours with 			stakeholders invited from 11.30 and lunch at 12.30.   Action:  Linda.

Lifespan of Implementation Group

Noted 1:	The group had a brief discussion about the anticipated lifespan of the 			Implementation Group and the Management Board  and agreed that this will

need to be considered in more depth at a future meeting.

11. 	Date of next meeting

The next meeting will be held on 26th August 2015, at 9.00 am at the Optima, Glasgow.