Date:		26 January 2017		Time:	13.30

Location:	 	Garnock Community Campus, North Ayrshire Council

1. 		Welcome and apologies

Present:		Ann Cura, Education Scotland (notes)

Bill Maxwell, Education Scotland (Chair)

Gill Stewart, Scottish Qualifications Authority

Jane Renton, Education Scotland

Ken Edwards, Skills Development Scotland

Steven Quinn, ADES

Denise Brock, Education Scotland

Murray McVicar, Scottish Government

Apologies:	Apologies from Michael Cross, Jean Blair, Andrew 	Bruce, Andrew Griffiths,  Alan 		Armstrong, Candy Munro, Diane Greenlees, Elizabeth Morrison and Maureen Gore.

Welcome:	N/A

2. 		Minutes and action log of the meeting held on 22 November 2016

Noted 1:		It was agreed that an amendment should be made to the Governance Review ( item 7, 		page 5) end date.  The closing date for the Governance Review date should read 6th 		January 2017.

Action 1: 		Ann Cura to update the minutes and arrange for them to be published online. (action 		023 on action log).

Noted 2: 		The group agreed that action in relation to the CfE Implementation Plan should be 		closed.  It was noted that a separate Implementation Plan will not be published but 		relevant actions will be integrated into the NIF improvement plan.  Actions 2-7 to 			remain open.

Action 2: 		Ann Cura to update the action log.  (action 001 on action log)

Noted 3:		The group discussed the action in relation to the headteacher conferences.  It was 		agreed that, given the rescheduling of the publication of the Benchmarks and the fact 		that a series of headteacher conferences on the Pupil Equity Fund was now planned 		for February 2017, that these events should now be scheduled for September 2017.

Action 3: 		Jane Renton to arrange a planning meeting with various stakeholders to discuss the 		agenda for these events. (action 024 on action log)

3. 		Matters arising

Noted 1: 		There were no matters arising.

4. 		Programme Reporting

4.1 		Programme Highlight Report

Noted 1:	The overall programme was on track for delivery according to plan.  There were a few 		missed milestones in the period. None of these missed milestones were judged likely 		to  have a significant	detrimental impact on the programme.

4.2 		Risk, Issues and Dependencies

Noted 1: 	The group reviewed the four red risks and agreed that these risks should remain red.

Noted 2:	The Senior Accountable Officers (SAO) Group proposed to add three new risks to the 		Risk Register. One in relation to the risk of continued negative publicity about Scottish 		education,  a second in relation to a risk of insufficient pace, rigour and depth of 			learning in the BGE resulting in inadequate preparation for Senior Phase and lastly a 		risk relating  to the very tight nature of the timelines of the revision programme for 		qualifications.	The group discussed the proposed risks and 	agreed that they should be 		added to the Risk Register.

Noted 3: 	It was noted that Risk 011 should be updated from Scottish Education to Curriculum 		for Excellence.  Also, it was noted that SAO group should propose mitigating actions 		for the new risks at the next Implementation Group meeting.

Action 4: 	Ann Cura to update the RID.  (action 030 on the action log)

Action 5:	SAO group to propose mitigating actions at the next Implementation Group Meeting.

Noted 4:	The SAO group proposed to reduce the probability of Risk 006.  This is due to			greater clarity provided by the publication of the National Improvement Plan (NIF).  		The group discussed this and agreed to this change.

Action 5:	Ann Cura to update the RID. (action 026 on the action log)

Noted 5:	The group discussed the Senior Phase and that there is risk that schools could return 		to a ‘minimum-change’ approach.  The group agreed that the wording of risk 008 			should be amended to reflect this and that the Benchmarks should be added as a 		mitigating action.

Action 6:	SAO group to propose new wording at the next Implementation Group Meeting. (action 		027 on the action log)

Noted 6:	The group discussed the risk owners and agreed the following changes:

Risk 002 –change to the Chair of the Implementation Group

Risk 004 – change to the Chair of the Implementation Group

Risk 010 –change to include College Development Network (CDN)

Action 7:	Ann Cura to update the RID. (action 028 on the action log)

Issues

Noted 1: 	The SAO group proposed to open a new Issue in relation to the publication of 			the CfE Benchmarks.

- risk of lack of support from professional associations for the development and implementation of Benchmarks beyond literacy and numeracy.

Noted 2:	The group discussed this and agreed that this should be added to the RID.

Action 8:	Ann Cura to update the RID. (action log 029 on the action log)

Noted 3:	The group discussed Issue 001 in relation to the negative publicity regarding the 			Benchmarks.  It was agreed that this should be reduced to an amber status.

Action 9:	Ann Cura to update the RID.  (action log 030 on the action log)

Dependencies

Noted 1:	No changes to the Dependencies Log.

5. 		SQA update

Noted 1:		Gill Stewart provided an update regarding the main projects that SQA are taking 	 		forward.

Noted 2:	The group noted that work is underway with Operations and Business Systems 			colleagues in SQA to establish what systems and operational changes will need to be 		made to support the implementation of the revisions to the qualifications.

Noted 3:	It was noted that SQA will send a letter to headteachers and key stakeholders to 			explain the changes.  The information for each subject will be published on each 			subject page and a summary document covering all subjects will be published on the 		NQ Changes page of 	SQA's website.

Noted 4:	It was also noted that a high-level document outlining how course assessment 			changes in session 17/18 will be published for teachers of each subject by the end of 		January 2017 and revised course arrangements will be published at the end of April 		2017.

6. 		Education Scotland Update

Development of Benchmarks

Noted 1:		It was noted that the publication of the Benchmarks has been delayed beyond 			the planned date of December 2016.  This was partly due to concerns raised by the 		EIS about benchmarks beyond literacy and numeracy.

At the request of Deputy First Minister, Education Scotland are holding a further 			meeting with EIS on 2 February 2017 to have further discussions on the format 			and publication of the Benchmarks.

7. 		Scottish Government Update

Assessment and National Qualifications Update

Noted 1:		Murray McVicar provided an update regarding the ANQ work.  At the last meeting held   		on 31 January 2017, the group had detailed discussions about the removal of unit 		assessments and changes to National 5 and 4. It is anticipated that a national 			guidance statement will be produced explaining to schools the nature and implications 		of the changes now being made. SG, ES and SQA are involved in drafting a 			statement.

Governance Review

Noted 2:     	The deadline for responses closed on 6th January 2017.  Over 11,000 written 			responses were received from a variety of stakeholders.  It was noted that over 700 		delegates attended various consultation events in relation the Governance Review.  A 		response from Scottish Government will be provided in due course.

Rationalisation of National Plans

Noted 3:	It was noted that since the meeting in November it has been agreed that that the 			National Improvement Framework (NIF) Improvement Plan, published in December 		2016,  means that there is no requirement for a 2017/18 CfE Implementation Plan.

Noted 4:	It was also noted that arrangements for governance of the actions contained in the 		NIF Improvement Plan should be clarified in due course through the Governance 			Review.

8. 		Foundation Apprenticeships

Noted 1:	Skills Development Scotland provided an update regarding Foundation 				Apprenticeships.  The group noted with interest the growth in this area.

Noted 2: 	The group noted with interest that a number of institutions view a Foundation 			Apprenticeship as a suitable entry for specific awards.

Noted 3: 	The group were asked how the benefits of Foundation Apprenticeships could be 			explained to parents and key partners. The group agreed that this should be discussed 		further at the next Implementation Group meeting.  It was agreed that it is important 		that choices/pathways are matched to the local job market.

Action 10:	Ann Cura to add Foundation Apprenticeships to the agenda for the next meeting. 		(action 031 on the action log)

9.  		Communications and Engagement

Noted 1:	It was noted that towards the end of 2016, various CfE delivery partners such as 			Education Scotland and SQA appeared in front of the Education and Skills Committee 		to discuss their role.  This generated a lot of media interest in Curriculum for 			Excellence.  This included a focus on the level of guidance that has been produced for 		education practitioners to support the implementation of CfE.

Noted 2: 		As a result of all the media interest, the Communications Group are planning to hold a 		workshop to draw up a communication plan.  Denise Brock will bring a draft 			communications plan to the next CfE Implementation Group in May 2017.

Action 11:		Denise Brock to propose communications plan at the next Implementation Group 		meeting.  (action 032 on the action log)

Noted 3: 	It was noted that Education Scotland’s National Improvement Hub is now ES’s key 		repository for	educational guidance and improvement materials, with the new 			corporate site carrying just corporate, programme and policy information.

10. 	        AOB

Stakeholder Session

Noted 1: 		The purpose of the consultation session was to give the Implementation Group direct 		access to feedback and perspective from this wider set of stakeholders as the Group 		proceeds to plan for the next phase of national support for implementation and benefits 		realisation of the CfE programme.

Noted 2:		It was noted that topics of discussion included the extent to which we have achieved 		the original aims of CfE; building more understanding of the success of CfE around the 		four capacities; assessment, tracking and monitoring, including the appropriate use of 		Benchmarks;  progress with Senior Phase curriculum models and the recent PISA 		results.

Action 12:		Ann Cura to draft a note from the Stakeholder Session. (action 033 on the action log)

11. 		Date of next meeting

The next meeting will be held on 10th May 2017.